## Sheet1
Task | Due Date | Status | Responsible | Additional info
Create architecture | 21/07/2015 | Completed | Atanas Georgiev | Uploaded in project\architecture
Create source structure | 22/07/2015 | Completed | Atanas Georgiev | Uploaded in project\src
Add laser implementation | tbd | Not started | tbd
Add game logic (fight target) | tbd | Not started | tbd
Improve object models | tbd | Not started | tbd
Add players and scoreBoard logic | tbd | Not started | tbd
Implement Game View (canvas) | tbd | Not started | tbd
Implement Score View (SVG) | tbd | Not started | tbd
Implement Controls View (html forms) | tbd | Not started | tbd
Code reviews | tbd | Not started | tbd | Correct naming Data encapsulation OOP and modules principles Strong cohesion and loose coupling
Add some unit tests | tbd | Not started | tbd
Add Jquery ?! | tbd | Not started | tbd
Update game documentation (MD file) | tbd | Not started | tbd
Backward compatibility ? | tbd | Not started | tbd