## Sheet1
Task | Due Date | Status | Responsible | Additional info
Create architecture | 21/07/2015 | Completed | Nasko | Uploaded in project\architecture
Create source structure | 22/07/2015 | Completed | Nasko | Uploaded in project\src
Add laser implementation | 26/07/2015 | Not started | Niki
Add game logic (fight target) | 26/07/2015 | Not started | Niki
Improve object models | 26/07/2015 | Not started | Mira
Add players and scoreBoard logic | 26/07/2015 | Not started | Valio
Implement Game View (canvas) | 26/07/2015 | Not started | Dimo
Implement Score View (SVG) | 26/07/2015 | Not started | Todor
Implement Controls View (html forms) | 26/07/2015 | Not started | Nasko
Code reviews | tbd | Not started | tbd | Correct naming Data encapsulation OOP and modules principles Strong cohesion and loose coupling
Add some unit tests | tbd | Not started | tbd
Add Jquery ?! | tbd | Not started | tbd
Update game documentation (MD file) | tbd | Not started | tbd
Backward compatibility ? | tbd | Not started | tbd